## Instructions
Implementation Business Case Template
Purpose This Business Case Template has been created to help applicants present a clear, proportionate business case for implementing a chosen innovation as part of the Water Innovation Implementation Programme. It is designed to support funding decisions, provide assurance that good practice has been followed, and create a practical foundation for delivery, monitoring and evaluation. When completing the template, you should consider the full life cycle of the innovation being implemented - not just the period of implementatin. This is required to ensure that the long-term benefits outweight the whole life cost of the solution, and that budget is planned to support the continued use of the solution post-implementation. Contents The Excel workbook is structured into four tabs, one for each area of the business case: - Economic Case (costs and benefits across the lifecycle, value for money) - Commercial Case (procurement routes/suppliers and capacity and capability to deliver) - Financial Case (budgets, spend profile by year, contingency and any shortfall) - Risks and Dependencies (key risks, mitigations and critical dependencies) Each tab includes guidance at the top on what good looks like and what assessors will expect to see. Who should complete it This workbook should be completed by the organisation applying for Implementation funding, drawing on input from relevant colleagues (e.g., operational leads, finance, procurement/commercial, delivery/project management, technical specialists and—where relevant—partners/suppliers). | How your business case will be used Your completed business case will be used to: - Inform funding decisions and assurance that the implementation is credible and value for money - Confirm your readiness and capability to implement successfully - Shape the implementation and support plan (e.g., milestones, dependencies, assurance points) - Provide a baseline for monitoring, evaluation and benefits realisation How to complete the workbook Please complete all four tabs, providing clear, evidence-based answers where possible. Keep responses concise and proportionate, but include enough detail for an independent reviewer to understand your rationale, assumptions, costs/benefits, delivery approach and risks. There are a number of formulas already populated in the spreadsheet. To ensure these continue to function please only add information to white cells
Submitting your Business Case Submit the completed Excel workbook as an attachment to your completed entry form to the innovationimplementation@isleutilities.com mailbox File name convention: OrgName_ImplementationBusinessCase (Excel and PDF)

## Summary
Implementation Business Case Template
Innovation name
Organisation
Author
Senior Responsible Owner (SRO)
Date
Innovation Overview | Total Cost (Whole Life) | 0
Copy the description of the innovation from your entry form (Q. 1.1.2)
Expected Life
▼ Add from implementation plan template
| Total Cost (Implementation) | 0
Implementation Duration
| Factored Benefits (Whole Life) | 0
Payback

## 1. Economic Case
Implementation Business Case Template
Innovation name | LeakLimit™
Organisation | Rivermere Water
Author | Joe Bloggs
Senior Responsible Owner (SRO) | Jemimma Jones
Date | 2026-01-29
GUIDANCE: | Economic Case
The Economic Case is the analytical heart of the business case: it demonstrates how the chosen solution will deliver value for money against the current baseline. Applicants should set out whole-life costs and benefits, showing with quantification (where possible) that the benefits outweigh costs over the lifecycle. A good business case also makes uncertainty explicit through risk and confidence considerations, so decision-makers can see what assumptions matter most.
Summary
Total Costs | 0
Total Benefit | 0
Net Benefit | 0
Total Benefit (Factored) | 0
Net Benefit (Factored) | 0 | This should be a positive value in order to demonstrate the total risk adjusted benefits outweight the total costs
Costs | Item | Description | Total | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Source of Data | Assumptions
Capital Expenditure
Applicants should list out all relelvant capital expenditure items across the lifespan of the solution. If this lifespan exceeds 10 years then the table should be extended accordingly. Additional rows can also be added as needed | Fixed assets |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0
| Software |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0
| Other Capital items |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0
| Total Capital costs (CAPEX) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Operating Expenditure
Applicants should list out all relelvant operational expenditure items across the lifespan of the solution. If this lifespan exceeds 10 years then the table should be extended accordingly. | Personnel |  | 0
| Personnel |  | 0
0
| Maintenance |  | 0
| Operating licences etc. |  | 0
| Training |  | 0
| Other Operating costs |  | 0
| Total Operating costs (OPEX) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contingency | [13 empty] | Justification
Add any cost contingency that is required across the innovations lifecycle | Contingency |  | 0
Total Solution Costs (CAPEX+OPEX) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Benefits | Item | Description | Total | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Source of Data | Assumptions | Confidence Level (%) | Justification
Main Benefits
| [Benefit 1] |  | 0
| [Benefit 2] |  | 0
| [Benefit 3] |  | 0
| [Benefit 4] |  | 0
| [Benefit 5] |  | 0
| [Benefit 6] |  | 0
| [Benefit 7] |  | 0
| [Benefit 8] |  | 0
| [Benefit 9] |  | 0
| [Benefit 10] |  | 0
| Total Benefits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Please include all assumptions that have been made in relation to the estimation of benefit value. This is critical for Fast Followers to understand if the same assumptions apply within their organisations (for example the estimated value of water lost may differ between companies)
| Total Benefits (Factored Value) | Adjusted for confidence level | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative Costs |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative Benefits |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumuluative Benefits (Factored) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Payback |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Payback (Factored) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
The year in which the cell turns green (positive value) indicates the year in which the cumulative benefits outweight the cumulative costs

## 2. Commercial Case
Implementation Business Case Template
Innovation name
Organisation
Author
Senior Responsible Owner (SRO)
Date
GUIDANCE: | Commercial Case
The Commercial Case explains how the organisation will procure and manage suppliers to deliver the implementation. Applicants should set out the procurement route(s) for each key item/package (e.g., framework, direct award where permitted, competition), identify the supplier(s) or supplier landscape and lead times, and map these to the delivery milestones needed to keep the implementation on track.
Procurement Routes | No. | Cost Item | Capex/Opex | Procurement Route | Supplier | Delivery Milestones
1
2
3
4
5
6
7
8
9

## 3. Financial Case
Implementation Business Case Template
Innovation name | LeakLimit™
Organisation
Author
Senior Responsible Owner (SRO)
Date
Section 4 | Financial Case
The Financial Case demonstrates affordability and funding: this should show that the implementation and the long-term support for the solution can be paid for within available budgets over time. Applicants should set out which budgets/funding sources will be used, profile expected spend by year, and identify any contingency, constraints, or shortfalls (and how these will be managed).
Budget Allocation | Funding Source | Description of funding source | Total | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10
▼ Add values for allocated budget in each year of the innovations life cycle. Budget allocation should match value of costs in that year
| Internal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capex |  | 0
| Opex |  | 0
| Non-regulated |  | 0
| Third-Party Funding |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Figures should align to what has been included in the detailed Implementation Plan Template (Appendix B) ▸ | Ofwat WIIP Funding | Value of funding requested from Ofwat's Water Innovation Implementation Programme | 0
| Other third-party funding | NA | 0
| TOTAL Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Budget |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
▼ The calculations below can be used when allocating your budget. If the cells are grey then the budgeted funds match the required costs
| Shortfall | Shows the shortfall in the budget to deliver required costs (this should be 0 at time of submission) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Surplus | Shows the surplus in the budget beyond planned costs (this should be 0 at time of submission) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 4. Risk Management
Implementation Business Case Template
Innovation name
Organisation
Author
Senior Responsible Owner (SRO)
Date
Section 5 | Risks & Dependencies
This section ensures the implementation is deliverable in practice by identifying the critical risks and dependencies that could prevent objectives being achieved, and how they will be managed. Applicants should highlight major strategic/delivery risks and summarise mitigations and monitoring arrangements in a risk register with likelihood, impact and severity calculated.
|  |  | Before Mitigation |  |  |  | After Mitigation
Strategic Risks | No. | Risk Definition | Likelihood (1 - 5) | Impact (1 - 5) | Severity (L x I) | Proposed Mitigation | Likelihood (1 - 5) | Impact (1 - 5) | Severity (L x I)
Outline your top 5 strategic risks and what mitigations you will take. | 1 |  |  |  | 0 |  |  |  | 0
| 2 |  |  |  | 0 |  |  |  | 0
| 3 |  |  |  | 0 |  |  |  | 0
| 4 |  |  |  | 0 |  |  |  | 0
| 5 |  |  |  | 0 |  |  |  | 0