## Instructions
Implementation Business Case Template
Purpose This Business Case Template has been created to help applicants present a clear, proportionate business case for implementing a chosen innovation as part of the Water Innovation Implementation Programme. It is designed to support funding decisions, provide assurance that good practice has been followed, and create a practical foundation for delivery, monitoring and evaluation. When completing the template, you should consider the full life cycle of the innovation being implemented - not just the period of implementatin. This is required to ensure that the long-term benefits outweight the whole life cost of the solution, and that budget is planned to support the continued use of the solution post-implementation. Contents The Excel workbook is structured into four tabs, one for each area of the business case: - Economic Case (costs and benefits across the lifecycle, value for money) - Commercial Case (procurement routes/suppliers and capacity and capability to deliver) - Financial Case (budgets, spend profile by year, contingency and any shortfall) - Risks and Dependencies (key risks, mitigations and critical dependencies) Each tab includes guidance at the top on what good looks like and what assessors will expect to see. Who should complete it This workbook should be completed by the organisation applying for Implementation funding, drawing on input from relevant colleagues (e.g., operational leads, finance, procurement/commercial, delivery/project management, technical specialists and—where relevant—partners/suppliers). | How your business case will be used Your completed business case will be used to: - Inform funding decisions and assurance that the implementation is credible and value for money - Confirm your readiness and capability to implement successfully - Shape the implementation and support plan (e.g., milestones, dependencies, assurance points) - Provide a baseline for monitoring, evaluation and benefits realisation How to complete the workbook Please complete all five tabs, providing clear, evidence-based answers where possible. Keep responses concise and proportionate, but include enough detail for an independent reviewer to understand your rationale, assumptions, costs/benefits, delivery approach and risks.
Submitting your Business Case Submit the completed Excel workbook as an attachment to your completed entry form to the innovationimplementation@isleutilities.com mailbox File name convention: OrgName_ImplementationBusinessCase (Excel and PDF)

## Summary
Implementation Business Case Template
Innovation name | LeakLimit™
Organisation | Rivermere Water
Author | Joe Bloggs
Senior Responsible Owner (SRO) | Jemimma Jones
Date | 2026-01-29
Innovation Overview |  | Total Cost (Whole Life) | 3947000
Copy the description of the innovation from your entry form (Q. 1.1.2)
|  | Expected Life | 10 years
▼ Add from implementation plan template
|  | Total Cost (Implementation) | 1735000
|  | Implementation Duration | 18 months
|  | Factored Benefits (Whole Life) | 8032500
|  | Payback | Year 3

## 1. Economic Case
Implementation Business Case Template
Innovation name | LeakLimit™
Organisation | Rivermere Water
Author | Joe Bloggs
Senior Responsible Owner (SRO) | Jemimma Jones
Date | 2026-01-29
GUIDANCE: | Economic Case
The Economic Case is the analytical heart of the business case: it demonstrates how the chosen solution will deliver value for money against the current baseline. Applicants should set out whole-life costs and benefits, showing with quantification (where possible) that the benefits outweigh costs over the lifecycle. A good business case also makes uncertainty explicit through risk and confidence considerations, so decision-makers can see what assumptions matter most.
Summary
Total Costs | 3947000
Total Benefit | 9315000
Net Benefit | 5368000
Total Benefit (Factored) | 8032500
Net Benefit (Factored) | 4085500 | This should be a positive value in order to demonstrate the total risk adjusted benefits outweight the total costs
Costs | Item | Description | Total | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Source of Data | Assumptions
Capital Expenditure
Applicants should list out all relelvant capital expenditure items across the lifespan of the solution. If this lifespan exceeds 10 years then the table should be extended accordingly. Additional rows can also be added as needed | Fixed assets |  | 917000 | 458500 | 458500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| LeakLimit™ Nodes (DMA & pressure points) |  | 558000 | 279000 | 279000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplier quote A.12 | 900 nodes @ £620 average (device + comms) incl. 2-yr warranty
| Trunk main high-resolution loggers |  | 114000 | 57000 | 57000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplier quote A.12 | 120 units @ £950 for critical corridors
| Installation/commissioning (capitalised) |  | 0 | 122500 | 122500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Framework contract E.34 - Installation and maintenance | Avg £240 per install incl. traffic mgmt and reinstatement where needed
| Software |  | 300000 | 200000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Analytics platform set-up (capitalised configuration) |  | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplier quote A.12 | £165k/year reduced for implementation
| Integration to GIS / work management / SCADA historian |  | 0 | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Framework contract E.12 - Telemetry and Control | Estimated cost based on previous project work conducted
| Cyber/security hardening (capitalised) |  | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Framework contract E.21 - IT & Cyber Security | Estimated cost based on previous project work conducted
| Other Capital items |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Capital costs (CAPEX) |  | 1217000 | 658500 | 558500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Operating Expenditure
Applicants should list out all relelvant operational expenditure items across the lifespan of the solution. If this lifespan exceeds 10 years then the table should be extended accordingly. | Personnel | PMO + data/IT + change lead time | 180000 | 90000 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Internal costs (change team) | 2.0 FTE average over 18 months, fully loaded
| Personnel | Leakage analytics + field support | 1320000 |  |  | 165000 | 165000 | 165000 | 165000 | 165000 | 165000 | 165000 | 165000 | Internal costs (leakage team) | 3.0 FTE equivalent, fully loaded £55k/FTE/yr
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Maintenance | Ongoing maintenance of field equipment (incl. spares) | 90000 | 0 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000
| Operating licences etc. | SaaS subscription + data hosting + SIM/data | 855000 | 0 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000
| Training | Training for operational staff | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other Operating costs | Travel, PPE, assurance sampling, comms | 270000 | 0 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000
| Total Operating costs (OPEX) |  | 2730000 | 105000 | 225000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
Contingency | [13 empty] | Justification
Add any cost contingency that is required across the innovations lifecycle | Contingency |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Solution Costs (CAPEX+OPEX) |  |  | 3947000 | 763500 | 783500 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
Benefits | Item | Description | Total | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Source of Data | Assumptions | Confidence Level (%) | Justification
Main Benefits
| Reduced leakage | 2.0 Ml/d saved = 730,000 m³/yr × £0.80/m³ marginal value (production + pumping + treatment) | 5256000 | 0 | 584000 | 584000 | 584000 | 584000 | 584000 | 584000 | 584000 | 584000 | 584000 | Performance as demonstrated through Trial Report 1.3D | 2.0 Ml/d saved = 730,000 m³/yr × £0.80/m³ marginal value (production + pumping + treatment). £0.80/m³ marginal value reflects RW’s high-level production/pumping/treatment marginal cost model (varies by WRZ). Leakage reduction is incremental and attributable, validated via matched control DMAs and seasonally adjusted baselines.No benefit in year 1 (during implementation) | 90% | Previous trial (see report 1.3D) demonstrated the technology was capable of lowering leakage within the trial DMA by 3.4ML/d. A conservative estimate has been applied here to accommodate for regional variation in leakage levels and leak types
| Reduced reactive repair & reinstatement | Fewer bursts/escalations due to earlier detection; 10% reduction in reactive jobs at avg £1,200/job | 1620000 | 0 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | Performance as demonstrated through Trial Report 1.3D | Fewer bursts/escalations due to earlier detection; 10% reduction in reactive jobs at avg £1,200/job. No benefit in year 1 (during implementation) | 85% | Previous trial demonstrated a 17% reduction in reactive jobs within the test area. Based on RW's current portfolio of planned and reactive work we believe this is an acheivable level across the region
| Fewer interruptions/compensation | 8% reduction in low-pressure/no-water incidents in priority zones; avoided payments and emergency response costs | 540000 | 0 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | Performance as demonstrated through Trial Report 1.3D | 8% reduction in low-pressure/no-water incidents in priority zones; avoided payments and emergency response costsNo benefit in year 1 (during implementation) | 70% | Previous trial results suggested that lower customer contacts were received during the trial however this was in a limited area and for a short period of time so lower confidence this will be achieved everywhere.
| Energy & chemical savings (incremental) | Included conservatively as additional to £0.80/m³ (captures avoidable peaks and pumping inefficiency reductions) | 594000 | 0 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | Extrapolated based on known operational expenditure for water production | Included conservatively as additional to £0.80/m³ (captures avoidable peaks and pumping inefficiency reductions). ODI value is conservative and annualised (recognising uncertainty and future incentive structures). No benefit in year 1 (during implementation) | 90% | If we are able to achieve the leakage reduction target this will have an additional benefit on water production costs
| ODI / performance risk reduction | Avoided leakage underperformance exposure (conservative annualised value) | 1080000 | 0 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | Based on ODI performance targets for AMP8 | Avoided leakage underperformance exposure (conservative annualised value). No benefit in year 1 (during implementation) | 75% | If we are able to achieve the leakage reduction target we should achieve our overal ODI target for the year. Lowered confidence due to other factors potentially impacting this target such as catastrophic failures
| Carbon reduction (valued) | ~250 tCO₂e/yr avoided × internal carbon value £100/t | 225000 | 0 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | Carbon Calculator (LINK) | ~250 tCO₂e/yr avoided × internal carbon value £100/t. No benefit in year 1 (during implementation) | 90% | If we are able to achieve the leakage reduction target this will have an additional benefit on capital and operational carbon
| [Benefit 7] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| [Benefit 8] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| [Benefit 9] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| [Benefit 10] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Benefits |  | 9315000 | 0 | 1035000 | 1035000 | 1035000 | 1035000 | 1035000 | 1035000 | 1035000 | 1035000 | 1035000 | Please include all assumptions that have been made in relation to the estimation of benefit value. This is critical for Fast Followers to understand if the same assumptions apply within their organisations (for example the estimated value of water lost may differ between companies)
| Total Benefits (Factored Value) | Adjusted for confidence level | 8032500 | 0 | 892500 | 892500 | 892500 | 892500 | 892500 | 892500 | 892500 | 892500 | 892500
Cumulative Costs |  |  |  | 763500 | 1547000 | 1847000 | 2147000 | 2447000 | 2747000 | 3047000 | 3347000 | 3647000 | 3947000
Cumulative Benefits |  |  |  | 0 | 1035000 | 2070000 | 3105000 | 4140000 | 5175000 | 6210000 | 7245000 | 8280000 | 9315000
Cumuluative Benefits (Factored) |  |  |  | 0 | 892500 | 1785000 | 2677500 | 3570000 | 4462500 | 5355000 | 6247500 | 7140000 | 8032500
Payback |  |  |  | -763500 | -512000 | 223000 | 958000 | 1693000 | 2428000 | 3163000 | 3898000 | 4633000 | 5368000
Payback (Factored) |  |  |  | -763500 | -654500 | -62000 | 530500 | 1123000 | 1715500 | 2308000 | 2900500 | 3493000 | 4085500
The year in which the cell turns green (positive value) indicates the year in which the cumulative benefits outweight the cumulative costs

## 2. Commercial Case
Implementation Business Case Template
Innovation name | LeakLimit™
Organisation | Rivermere Water
Author | Joe Bloggs
Senior Responsible Owner (SRO) | Jemimma Jones
Date | 2026-01-29
GUIDANCE: | Commercial Case
The Commercial Case explains how the organisation will procure and manage suppliers to deliver the implementation. Applicants should set out the procurement route(s) for each key item/package (e.g., framework, direct award where permitted, competition), identify the supplier(s) or supplier landscape and lead times, and map these to the delivery milestones needed to keep the implementation on track.
Procurement Routes | No. | Cost Item | Capex/Opex | Procurement Route | Supplier | Delivery Milestones
| 1 | LeakLimit™ Nodes & trunk loggers (fixed assets) | Capex | Under RW telemetry / monitoring framework (or open tender if required) | TBC | M3: ITT issued → M5: award → M9: first 50 DMAs live → M18: 100% rollout
| 2 | Installation & commissioning | Capex | Call-off from RW network services / civils framework (regional lots) | Tier-2 civils partners and term maintenance contractors | M6: install packs approved → M7–M18: phased installs by region
| 3 | Integration to GIS / work management / SCADA historian | Capex | Call-off from RW IT integration framework | TBC | M4: interface design → M8: integration tested → M12: automated work order flow
4
5
6
7
8
9

## 3. Financial Case
Implementation Business Case Template
Innovation name | LeakLimit™
Organisation | Rivermere Water
Author | Joe Bloggs
Senior Responsible Owner (SRO) | Jemmima Jones
Date | 2026-01-29
Section 4 | Financial Case
The Financial Case demonstrates affordability and funding: this should show that the implementation and the long-term support for the solution can be paid for within available budgets over time. Applicants should set out which budgets/funding sources will be used, profile expected spend by year, and identify any contingency, constraints, or shortfalls (and how these will be managed).
Budget Allocation | Funding Source | Description of funding source | Total | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10
▼ Add values for allocated budget in each year of the innovations life cycle. Budget allocation should match value of costs in that year
| Internal |  | 3173500 | 263500 | 510000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
| Capex | Planned asset renewal funding for AMP8 will be used to partially fund the solution implementation | 548500 | 263500 | 285000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Opex | Regional leakage budgets will be used to fund on-going operational costs post-implementation | 2625000 |  | 225000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
| Non-regulated | Non-regulated funds will also be used to provide a portion of total funding | 0
| Third-Party Funding |  | 773500 | 500000 | 273500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Figures should align to what has been included in the detailed Implementation Plan Template (Appendix B) ▸ | Ofwat WIIP Funding | Value of funding requested from Ofwat's Water Innovation Implementation Programme | 773500 | 500000 | 273500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other third-party funding | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Costs |  | 3947000 | 763500 | 783500 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
| TOTAL Budget |  | 3947000 | 763500 | 783500 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
▼ The calculations below can be used when allocating your budget. If the cells are grey then the budgeted funds match the required costs
| Shortfall | Shows the shortfall in the budget to deliver required costs (this should be 0 at time of submission) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Surplus | Shows the surplus in the budget beyond planned costs (this should be 0 at time of submission) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 4. Risk Management
Implementation Business Case Template
Innovation name | LeakLimit™
Organisation | Rivermere Water
Author | Joe Bloggs
Senior Responsible Owner (SRO) | Jemmima Jones
Date | 2026-01-29
Section 5 | Risks & Dependencies
This section ensures the implementation is deliverable in practice by identifying the critical risks and dependencies that could prevent objectives being achieved, and how they will be managed. Applicants should highlight major strategic/delivery risks and summarise mitigations and monitoring arrangements in a risk register with likelihood, impact and severity calculated.
|  |  | Before Mitigation |  |  |  | After Mitigation
Strategic Risks | No. | Risk Definition | Likelihood (1 - 5) | Impact (1 - 5) | Severity (L x I) | Proposed Mitigation | Likelihood (1 - 5) | Impact (1 - 5) | Severity (L x I)
Outline your top 5 strategic risks and what mitigations you will take. | 1 | Benefits don’t materialise at scale | 2 | 4 | 8 | In M0–M2 we will agree a signed baseline and simple attribution method per DMA (alert → investigation → confirmed leak → repair → verified night-flow step change) and publish a short Benefits Measurement Plan. By M2–M4 we will create practical playbooks for the main alert types and validate assumptions in a controlled pilot (M6–M9) using test and matched control DMAs. During roll-out (M9–M24) we will run a weekly alert-to-action review tracking 48-hour triage, investigation starts, close-outs and verified Ml/d saved; if savings fall below 70% of run-rate for two months from M12 onward we will trigger a reset (commissioning checks, threshold re-tuning and targeted retraining) until performance recovers, with benefits confirmed at M24–M36. | 1 | 3 | 3
| 2 | IT/OT integration delays | 2 | 3 | 6 | In M0–M1 we will appoint named IT and OT integration leads and run a weekly governance forum with a single backlog and clear decision rights. By M1–M3 we will lock the target architecture and data standards, then de-risk delivery in M3–M6 via a sandbox and a “thin slice” integration (alerts creating work orders end-to-end) before scaling. Roll-out will proceed with an agreed manual workaround only if needed, but by M12 at least 80% of high-confidence alerts must flow automatically into work management for deployed regions or further expansion pauses. Cyber approvals will be built in early, with pen-test at M6 and remediation complete by M8. | 1 | 2 | 2
| 3 | Data quality / coverage issues | 3 | 2 | 6 | From M2–M6 we will complete site/connectivity surveys and issue standard install packs to prevent dead spots and inconsistent tagging. Every device will be commissioned against acceptance criteria (correct GIS/DMA tagging, stable telemetry, timestamp integrity, minimum completeness) during M6–M18, supported by automated QA checks and weekly threshold-tuning through M24 to cut false alerts. From M9 onward we will enforce an estate SLA of ≥98% data availability, hold spares locally and swap failed units within 5 working days, with monthly reviews of recurring data issues feeding directly into updated standards and installer retraining. | 2 | 1 | 2
| 4 | Supply chain lead times | 3 | 1 | 3 | We will procure early (M2–M5) with committed delivery schedules for pilot and first roll-out regions, clear acceptance tests and remedies for late delivery. Between M2–M6 we will specify interoperability to enable dual sourcing where feasible and require contingency evidence where not, then protect the schedule with buffer stock and a phased regional roll-out (M6–M18) prioritising the leakiest DMAs first. From M5 onward we will run monthly supplier performance reviews, and we will pre-agree scope levers (M2–M4) so any cost pressure triggers quantified change control that preserves core coverage and benefits. | 2 | 1 | 2
| 5 | Operational adoption resistance | 2 | 4 | 8 | In M1–M4 we will co-design the triage-to-repair workflow with frontline teams, agree a clear RACI and convert this into SOPs and job aids. We will stand up regional “champions” (M4–M18) and deliver role-based train-the-trainer training (M9–M18) with competency sign-off for key users. From M12 onward we will make LeakLimit™ the default input to weekly leakage planning and track simple adoption KPIs (alerts triaged/actioned within set times), reinforced through monthly performance reviews; where adoption slips we will deploy targeted coaching and remove process friction rather than relying on one-off comms. | 2 | 3 | 6